## Critical Path
Community Games
Timeline
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Key contacts and finance
Identify stakeholders and key contacts | All | Completed
Open bank account | NT | Completed
Research where to access/apply for funds | NT | Completed
Research local sponsorship opportunities | NT | On track
Set event budget | NT | On track
Obtain quotes for venues and equipment if necessary | JM | On track
Create monitoring budget template | MH | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Planning your Community Games
Produce timeline document | NT | Completed
Research dates for Community Games | NT | Completed
Set date for Community Games | NT | On track
Research venues | MH | On track
Book venue | MH | On track
Check event licenses required | NT | On track
Apply for licenses required | NT | On track
Write event delivery plan | NT | On track
Ensure sustainable practices are adopted | ALL | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Sports Activities
Research Sports Clubs in your community | NT | On track
Invite local sports clubs to offer taster sessions | NT | On track
Research and recruit officials to assist with on the day management of sports | JM | On track
Create Sports/Activity programme | NT | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Cultural Events
Set up Cultural Events sub committee | MH | Completed
Research activities that may interest your community | MH | Completed
Contact local groups | MH | On track
Create Cultural Events programme | MH | On track
Plan Community Games opening/closing ceremonies | MH | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Volunteers
Create Volunteer plan | JR | On track
Research where volunteers could be recruited | JR | On track
Advertise volunteer opportunities | JR | On track
Recruit volunteers | JR | On track
Volunteer training/briefing | JR | On track
Thank you party for volunteers | JR | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Production and Logistics
Create site plans | NT | On track
Obtain quotes where necessary using RFQs | NT | On track
Create production schedule | NT | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Marketing and PR
Research target audience | LB | Completed
Write marketing plan | LB | On track
Contact local schools/groups/shops to request to display marketing materials | LB | On track
Contact local printers to obtain quotes/request in kind support for Community Games | LB | On track
Produce flyers/posters | LB | On track
Distribute materials | LB | On track
Create Facebook page - and update | LB | On track
Create Twitter page - and update | LB | On track
Add email banner to signatures of organisers outgoing emails. | LB | On track
Compile a list of local media | LB | On track
Inform local media of Community Games | LB | On track
Launch of Community Games | LB | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Health and Safety
Complete Risk Assessment | NT | On track
Research First Aid cover | NT/DL | On track
Arrange external first aid cover if required | NT | On track
Research venue insurance | NT | On track
Arrange required event insurance policies | NT | On track
Write Emergency Plan | NT | On track
Area | Resp. | Completed? | Date | 2010-06-07 | 2010-06-14 | 2010-06-21 | 2010-06-28 | 2010-07-05 | 2010-07-12 | 2010-07-19 | 2010-07-26 | 2010-08-02 | 2010-08-09 | 2010-08-16 | 2010-08-23 | 2010-08-30
Evaluating your Community Games
Receive event cards from WM for 2012 | NT | On track
Print hard copies of participant questionnaires for distribution on day of Community Games |  | On track
Distribute cards at Community Games | NT | On track
Undertake volunteer feedback at thank you party | NT | On track
Complete organisers online questionnaire | NT | On track
Send hard copies of questionnaires back to WM for 2012 | NT | On track
Completed
On track
Not started
Urgent